VDOT Contract - Partnering Guidelines

| Contract Category | Approximate Contract Duration | Typical Contract Complexity | Example Contract Type(s) | Recommended Partnering Level |
| --- | --- | --- | --- | --- |
| I | <12 months | Low complexity, Single season-short duration, Favorable operations and conditions | Rehab projects, Minor drainage work, Widening & overlays, Paving schedules | D |
| II | <12 months | Low to medium complexity, Single season, Typical operations and conditions | Minor reconstruction, Major drainage work, Minor intersections | C or D |
| III | <36 months | Medium complexity, Multi-season, Typical operations and conditions | Major reconstruction, New construction, Major intersections | B or C |
| IV | >36 months | Medium to high complexity, Multi-season, Challenging operations and conditions | Large single contracts, Major improvements | A or B |
| V | >36 months | High complexity, Multi-season-long duration, Challenging operations and conditions | Large major contracts, Multiple major contracts, Major improvements | A |

Partnering Levels

| Level | Partnering Type | Characteristics | Partnering Facilitator |
| --- | --- | --- | --- |
| A | Formal | Kick-off Workshop (typically 1 to 2 Days); monthly partnering meetings; requires external objectivity; rating forms used | * Contract Facilitator |
| B | Formal | Kick-off Workshop (typically 1 Day); at a minimum, quarterly partnering meetings; requires external objectivity; rating forms used | * Contract Facilitator |
| C | Informal | Initial Partnering Meeting (typically 1/2 to 1 Day); at a minimum, semi-annual partnering meetings; optional external objectivity & rating forms | VDOT or * Contract Facilitator |
| D | Informal | Initial Partnering Meeting typically conducted during/after pre-con meeting, subsequent partnering will be part of progress meetings | VDOT Project Manager w/ Contractor Personnel |

* Note:  On a project by project basis, facilitator selection will be based on industry experience and individual knowledge, skills, and abilities to match project requirements.  Facilitator selection is a joint decision between VDOT and the Contractor and is a bid pay item in the contract. The DCE and/or ACE are regarded as the responsible charge VDOT positions for Partnering.  In most cases, the State Partnering Coordinator will be consulted on matters pertaining to partnering levels, facilitator selection, workshop planning, and rating form usage.